## Sheet1
PRODUCT BACKLOG
| User Story | Complexity | ESTIMATE | CONVERSATION | STATUS
| As a user, I can view all data from the data set, so that I can find any information I might want to know about the hospital | 10 | 9 | View by view – important bits are distance, price, name of hospital. If user is looking for distance then maybe a different view but find a way to limit this information. | In progress
| As a user, I can search using a location to find all the hospitals that are close to that location, so that I can narrow my search | 8 | 2 |  | Complete
| As a user, I can view my results based on the distance from my input location, so that I can find the closest hospitals | 7 | 2 |  | Complete
| As a user, I can view my search results in an ordered list based on the highest/lowestprice, so that I can quickly find the cheapest/most expensive hospital | 7 | 2 |  | Complete
| As a Centers for Medicare & Medicaid manager, I can load new data to the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 3(optional) | 7 | User experience, interaction, searching, more filtering is more important than editing datasets. Better to split the UIs – User UI is much more important than admin UI. | Not started
| As a Centers for Medicare & Medicaid manager, I can delete data from the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 3(optional) | 7 |  | Not started
| As a Centers for Medicare & Medicaid manager, I can delete data from the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 3(optional) | 7 |  | Not started
| The user can restrict their search to a price range, so that the user can find the cheapest options available | 6 | 5 |  | Complete
| As a user, I can restrict my search to a distance range, so that I don't have to wait as long for search results as there will be less results | 6 | 5 |  | Complete
| The user's location can be derived from user input | 7 | 3 |  | Complete
| The user's location can be derived from device location | 5 | 3 |  | Not started
| The user can view the results as a ranked list, based on a combination of information | 3(optional) | 7 | That’d be ideal. Don’t overload customer with too much information. Block out the “most boring” ones. | In progress
| The product should be accessible by all user groups | 4 (optional) | 8 | Important to a degree but would rather have a nice UI, nice user experience than accessibility. If it’s very costly to do this now, could make a start but doesn’t have to be done straight away. For this sprint, not too important. For product, implement later | Not started
| software can provide machine learning based on user selection | 2 (optional) | 10 | If there’s time then great – Not on top of their list. Get the search, filtering etc. down to a T before starting on machine learning. Would be nice but beyond their expectations for the project… for now. | Not started
| As a user, I can locate a suitable hospital at a glance, so that I can quickly make a decision on waht hospital is the best choice for me, I spend less time searching for a hospital - using a map | 6 | 9 | How should the pins look? Any preferences? Up to us – if we have good ideas to improve user experience then go for it but they’ve not got any specific preferences. Would be nice to see some distinction. | In progress
| As a user, I can view additional details for my search results, so that I don't have to visit another search page to find out more information | 7 | 7 |  | Not started
| As a user, I can search for a procedure code and find all the hospitals that perform that procedure, so that I can narrow my search | 9 | 2 |  | completed
| As a user, I can search for the name of a procedure and find all the hospitals that perform that procedure, so that I can narrow my search | 9 | 2 |  | completed