## Sheet1
Sprint Burndown |  |  | 2020-02-03 | 2020-02-04 | 2020-02-05 | 2020-02-06 | 2020-02-07
User Stories/Tasks | Initial Estimate | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Display a combination of search results in one list | 5 |  |  |  |  | 2
Develop website interface to be more simple and helpful for the user | 3 |  |  | 3
Test merge functionality using TDD - call Java functions from the web page | 3 |  | 3
Test recieving data from Java function calls puling from the database | 3 |  |  | 3
Test displaying data recieved from Java function calls | 5 |  |  |  | 3 | 2
Merge functional map into HTML using TDD - added 30/01/2020 to add more detail and break up the task | 5
Merge HTML front end with back end search function using TDD: search by code, distance, procedure | 5
Merge HTML front end with back end search function: restrict search by distance, price | 1
Merge HTML front end with back end search function: order by price, distance | 2
Create a function to add data to the existing data set | 2 |  |  | 2
Create a function to delete the existing data set | 3 |  |  |  | 2
Create a function to edit the existing data set | 2
Corrolate search results with map pins | 5 |  | 2 | 1
Display additional details for search results | 2
Create an option to use the device's location as input for searches using location | 2 |  |  |  | 2
Merge all tasks together
[8 empty] | Legend: | Missing at Start | Velocity 1 | Velocity 2
[9 empty] | Added to Sprint later | 50
| Remaining Effort | 48 | 43 | 34 | 27 | 23 | 23 |  | Projected Value
| Ideal Trend | 48 | 48 | 36 | 24 | 12 | 0
| Story points (1) | Name
| 2 hours | Tony
| 2 hours | Dimitar
| 2 hours | Jodie
| 2 hours | Tony
| 2 hours | Michael
| 2 hours | Joel