## Agile Product Backlog
SPRINT BACKLOG | [9 empty] | 1 Story = 2 Hours
SPRINT # | TASK NAME | User Story | Complexity | PRIORITY | Return on Investment | ASSIGNED TO | STORY POINTS | START | FINISH | STATUS | Date comlpeted | Velocity 1 | Velocity 2
Sprint 2 | [11 empty] | 75
| Display a combination of search results in one list | As a user, I can view the results as a ranked list based on a combination of information, so that I can find the best choice to suit my personal needs | 5 | 3 | 0.6 | Tony, Dimitar | 2 | 2020-04-02 | 2020-05-02 | In Progress |  | This section is for the drop-down list
| Develop website interface to be more simple and helpful for the user | As a user, I can use the website almost as quick the first time as the 50th time using the website, so that as an new user, I can use the website quickly and with ease | 2 | 6 | 3 | Tony | 3 | 2020-04-02 | 2020-05-03 | In Progress |  | Yes | High | Complete
| Merge all tasks together |  | 3 | 10 | 3.3333 | All |  | 2020-04-02 | 2020-05-02 | In Progress
| Merge functional map into HTML - added 30/01/2020 to add more detail and break up the task |  | 8 | 9 | 1.125 | Tony, Michael | 8 | 2020-04-02 | 2020-05-02 | Complete
| Merge HTML front end with back end search function: search by code, distance, procedure |  | 3 | 9 | 3 | All | 5 | 2020-03-02 | 2020-05-02 | In Progress
| Merge HTML front end with back end search function: restrict search by distance, price |  | 4 | 9 | 2.25 | All | 5 | 2020-04-02 | 2020-05-02 | In Progress
| Merge HTML front end with back end search function: order by price, distance |  | 4 | 9 | 2.25 | All | 5 | 2020-04-02 | 2020-05-02 | In Progress
| Corrolate search results with map pins |  | 3 | 7 |  | Michael | 3 | 2020-03-01 | 2020-04-01 | In Progress
| Display additional details for search results | As a user, I can view additional details for my search results, so that I don't have to visit another search page to find out more information | 3 | 7 | 2.3333 | Joel | 2 | 2020-03-02 | 2020-04-02 | Not Started
| Create an option to use the device's location as input for searches using location | As a user, I can use my device's location as an input for the search, so that I can save time and don't need to know the address, state or zip code location I am currently at | 3 | 5 | 1.6667 | Dimitar | 1 | 2020-05-02 | 2020-06-02 | Not Started
| Add screen reader functionality | As a user, I can use a screen reader to read the page, so that I can still use the website if I have a visual imparement | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started |  | No | Medium | In Progress
| Add text resize options | As a user, I can resize the text, so that I can make it bigger/smaller to suit my needs | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Add text/image colour options | As a user, I can change the colours used on the web page, so that can still use the website if I have a visual imparement | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Create a function to add data to the existing data set | As a Centers for Medicare & Medicaid manager, I can load new data to the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 2 | 3 | 1.5 | Ben | 1 | 2020-05-02 | 2020-06-02 | Not Started
| Create a function to delete the existing data set | As a Centers for Medicare & Medicaid manager, I can delete data from the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 2 | 3 | 1.5 | Ben | 2 | 2020-05-02 | 2020-06-02 | Not Started
| Create a function to edit the existing data set | As a Centers for Medicare & Medicaid manager, I can delete data from the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 2 | 3 | 1.5 | Ben | 2 | 2020-05-02 | 2020-06-02 | Not Started
| Merge all tasks together |  | 2 | 10 | 5 | Jodie, Tony, Joel, Ben | 8 | 2020-06-02 | 2020-07-02 | Not Started

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.