## Agile Product Backlog
SPRINT BACKLOG | [9 empty] | 1 Story = 2 Hours
SPRINT # | TASK NAME | User Story | Complexity | PRIORITY | Return on Investment | ASSIGNED TO | STORY POINTS | START | FINISH | STATUS | Date comlpeted | Velocity 1 | Velocity 2
Sprint 1 | [11 empty] | 75
| Create the website, include all input fields | As a user, I can view all data from the data set, so that I can find any information I might want to know about the hospital | 3 | 10 | 3.3333 | Tony, Joel, Michael | 8 | 27/01/20 | 28/01/20 | Complete | 27/01/20 | This section is for the drop-down list
| Display data set front end template (updated 29th to break up tasks as the database was not ready to take data from) |  | 2 | 10 | 5 | Tony, Joel | 4 | 27/01/20 | 28/01/20 | Complete | 30/01/20 | Yes | High | Complete
| Display data set |  | 2 | 10 | 5 | Tony, Joel, Dimitar | 4 | 28/01/20 | 29/01/20 | In Progress | ..
| Create a database (added 28th when we decided to use an sql database to search through the dataset as it is so large) |  | 1 | 10 | 10 | Jodie | 1 | 28/1/20 | 28/1/20 | Complete | 28/01/20
| Populate database |  | 3 | 10 | 3.3333 | Jodie, Michael | 3 | 28/1/20 | 28/1/20 | Complete | 29/01/20
| Include a map on the website | As a user, I can locate a suitable hospital at a glance, so that I can quickly make a decision on waht hospital is the best choice for me, I spend less time searching for a hospital | 3 | 9 | 3 | Michael | 4 | 27/01/20 | 28/01/20 | Complete | 29/01/20
| Set up display icon pins (displaying relevant data at the relevant location) - added 30/01/2020 to add more detail and break up the task |  | 3 | 8 | 2.6667 | Michael | 4 | 29/01/20 | 30/01/20 | Complete | 30/01/20
| Create search by code function | As a user, I can search for a procedure code and find all the hospitals that perform that procedure, so that I can narrow my search | 2 | 9 | 4.5 | Ben | 4 | 27/01/20 | 28/01/20 | Complete | 28/01/20
| Create search by procedure function | As a user, I can search for the name of a procedure and find all the hospitals that perform that procedure, so that I can narrow my search | 2 | 9 | 4.5 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 28/01/20
| Create search by location function | As a user, I can search using a location to find all the hospitals that are close to that location, so that I can narrow my search | 2 | 8 | 4 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 28/01/20
| Create an order by distance function | As a user, I can view my results based on the distance from my input location, so that I can find the closest hospitals | 3 | 7 | 2.3333 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 30/01/20 | No | Medium | In Progress
| Create an order by price function | As a user, I can view my search results in an ordered list based on the highest/lowestprice, so that I can quickly find the cheapest/most expensive hospital | 3 | 7 | 2.3333 | Ben | 2 | 28/01/20 | 29/01/20 | Complete | 28/01/20
| Calculate distance between two locations | As a user, I can restrict my search to a distance range, so that I don't have to wait as long for search results as there will be less results | 2 | 6 | 3 | Jodie | 3 | 29/01/20 | 30/01/20 | Complete | 28/01/20
| Create function to restrict search to a distance range |  | 1 | 6 | 6 | Jodie | 2 | 29/01/21 | 30/01/21 | Complete | 28/01/20
| Create function to restrict search to a price range | As a user, I can restrict my search to a price range, so that I don't have to wait as long for search results | 3 | 6 | 2 | Jodie | 2 | 29/01/20 | 30/01/20 | Complete | 27/01/20
| Link java functions to SQL database - added 30/01/2020 to add more detail and break up the task |  | 4 | 10 | 2.5 | Jodie | 5 | 30/01/20 | 31/01/20 | Complete | 29/01/20
| Call java functions from HTML - added 30/01/2020 to add more detail and break up the task |  | 4 | 10 | 2.5 | Tony, Joel | 5 | 30/01/20 | 31/01/20 | Complete | 30/01/20
| Merge all tasks together |  | 3 | 10 | 3.3333 | All |  | 30/01/20 | 31/01/20 | In Progress | ..
| Merge functional map into HTML - added 30/01/2020 to add more detail and break up the task |  | 8 | 9 | 1.125 | Tony, Michael | 8 | 30/01/21 | 31/01/21 | In Progress | ..
| Merge HTML front end with back end search function: search by code, distance, procedure |  | 3 | 9 | 3 | All | 5 | 30/01/22 | 31/01/22 | In Progress | ..
| Merge HTML front end with back end search function: restrict search by distance, price |  | 4 | 9 | 2.25 | All | 5 | 30/01/23 | 31/01/23 | In Progress | ..
| Merge HTML front end with back end search function: order by price, distance |  | 4 | 9 | 2.25 | All | 5 | 30/01/24 | 31/01/24 | In Progress | ..
Sprint 2 | [6 empty] | 80 | [5 empty] | Low | Not Started
| Display a combination of search results in one list | As a user, I can view the results as a ranked list based on a combination of information, so that I can find the best choice to suit my personal needs | 5 | 3 | 0.6 | Dimitar | 2 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge all tasks together |  | 3 | 10 | 3.3333 | All |  | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge functional map into HTML - added 30/01/2020 to add more detail and break up the task |  | 8 | 9 | 1.125 | Tony, Michael | 8 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge HTML front end with back end search function: search by code, distance, procedure |  | 3 | 9 | 3 | All | 5 | 2020-03-02 | 2020-05-02 | In Progress | ..
| Merge HTML front end with back end search function: restrict search by distance, price |  | 4 | 9 | 2.25 | All | 5 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Merge HTML front end with back end search function: order by price, distance |  | 4 | 9 | 2.25 | All | 5 | 2020-04-02 | 2020-05-02 | In Progress | ..
| Intergrate search results into map |  |  |  |  | Michael |  | 2020-03-01 | 2020-04-01 | In Progress
| Include a map with placeholder for all search results | As a user, I can see search results indicated on the map using a placeholder, also displaying extra information, so that I don't need to find the hospital in the list of search results to find out more about it if I first see it on the map | 3 | 6 | 2 | Tony, Michael | 2 | 2020-03-02 | 2020-04-02 | Not Started
| Display name of establishment, location and price when mouse over placeholder |  | 2 | 6 | 3 | Tony, Michael | 4 | 2020-04-02 | 2020-05-02 | Not Started
| Display additional details for search results | As a user, I can view additional details for my search results, so that I don't have to visit another search page to find out more information | 3 | 7 | 2.3333 | Jodie | 2 | 2020-03-02 | 2020-04-02 | Not Started
| Create an option to use the device's location as input for searches using location | As a user, I can use my device's location as an input for the search, so that I can save time and don't need to know the address, state or zip code location I am currently at | 3 | 5 | 1.6667 | Tony | 1 | 2020-05-02 | 2020-06-02 | Not Started
| Add screen reader functionality | As a user, I can use a screen reader to read the page, so that I can still use the website if I have a visual imparement | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Add text resize options | As a user, I can resize the text, so that I can make it bigger/smaller to suit my needs | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Add text/image colour options | As a user, I can change the colours used on the web page, so that can still use the website if I have a visual imparement | 1 | 4 | 4 | Joel | 1 | 2020-04-02 | 2020-05-02 | Not Started
| Create a function to add data to the existing data set | As a Centers for Medicare & Medicaid manager, I can load new data to the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 2 | 3 | 1.5 | Ben | 1 | 2020-05-02 | 2020-06-02 | Not Started
| Create a function to delete the existing data set | As a Centers for Medicare & Medicaid manager, I can delete data from the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 2 | 3 | 1.5 | Ben | 2 | 2020-05-02 | 2020-06-02 | Not Started
| Create a function to edit the existing data set | As a Centers for Medicare & Medicaid manager, I can delete data from the existing dataset through the website, so that; when the dataset is updated, I can easily update the databse | 2 | 3 | 1.5 | Ben | 2 | 2020-05-02 | 2020-06-02 | Not Started
| Record user input data |  | 1 | 2 | 2 | Jodie | 2 | 2020-04-02 | 2020-07-02 | Not Started
| Analyse data and look for patterns/trends | Software can provide machine learning based on user selection, so that Improvements can be made based on website usage | 4 | 2 | 0.5 | Jodie | 4 | 2020-04-02 | 2020-07-02 | Not Started
| Output relevent data based on analysis |  | 2 | 2 | 1 | Jodie | 3 | 2020-04-02 | 2020-07-02 | Not Started
| Merge all tasks together |  | 2 | 10 | 5 | Jodie, Tony, Joel, Ben | 4 | 2020-06-02 | 2020-07-02 | Not Started
| Create button to resize text |  | 3 | 3 | 1 | Dimitar
| Add accesibility compatability |  | 1 | 6 | 6 | Dimitar

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.